## MRS
Group 1 - Gantt Chart | [15 empty] | 0
| Group | Glenn10 |  |  | DEPARTMENT |  |  |  | Computer Engineering
| SEMESTER | 2nd Semester |  |  | SY |  |  |  | 2025-2026
ID | TASK | START DATE | END DATE | STATUS | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13 | [6 empty] | WEEK 14 | [6 empty] | WEEK 15 | [6 empty] | WEEK 16 | [6 empty] | WEEK 17 | [6 empty] | WEEK 18
 | time axis 2025-11-29 to 2026-04-17
1 | Planning Phase | [129 empty] | Ratings Of Design | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | time axis 2025-11-29 to 2026-04-17
1.1 | Brainstorming | 2025-11-29 | 2025-12-13 | Done | [126 empty] | Design 1 | bar: 2025-11-29 to 2025-12-06
1.2 | Researching | 2025-11-29 | 2025-12-13 | Done | [126 empty] | Design 2 | bar: 2025-11-29 to 2025-12-06
1.3 | Conceptualization | 2025-11-29 | 2025-12-13 | Done | [126 empty] | Design 3 | bar: 2025-11-29 to 2025-12-06
1.4 | Searching for possible client | 2025-11-29 | 2025-12-13 | Done | bar: 2025-11-29 to 2025-12-06
1.5 | Background checking of the possible client | 2025-12-06 | 2025-12-13 | Done | bar: 2025-11-29 to 2025-12-13
2 | Requirements
2.1 | Making of survey | 2025-12-06 | 2026-01-10 | Done | bar: 2025-12-06 to 2025-12-13
2.2 | Selecting of the client | 2025-12-06 | 2026-01-10 | Done | bar: 2025-12-06
2.3 | Dissemination of survey forms | 2025-12-06 | 2026-01-10 | Done | bar: 2025-12-06 to 2025-12-18
2.4 | Interviewing the client | 2025-12-06 | 2026-01-10 | Done | bar: 2025-12-06 to 2025-12-18
2.5 | Analyzing and interpreting the data | 2025-12-06 | 2026-01-10 | Done | bar: 2025-12-06 to 2026-01-10
3 | Design Phase
3.1 | Algorithm | 2026-01-10 | 2026-01-24 | Done | bar: 2026-01-10 to 2026-01-24
3.2 | Flowchart | 2026-01-10 | 2026-01-24 | Done | bar: 2026-01-10 to 2026-01-24
3.3 | DFD (Data Flow Diagram) | 2026-01-10 | 2026-01-24 | Done | bar: 2026-01-10 to 2026-01-24
3.4 | ERD (Entrity-Relationship Diagram) | 2026-01-10 | 2026-01-24 | Done | bar: 2026-01-10 to 2026-01-24
3.5 | Storyboarding | 2026-01-10 | 2026-01-24 | Done | bar: 2026-01-10 to 2026-01-24
4 | Development Phase
4.1 | HTML and PHP Coding of User Interface | 2026-12-07 | 2026-03-28 | Done | bar: 2025-12-07 to 2026-03-29
4.2 | HTML and PHP Coding Front End | 2026-12-07 | 2026-03-28 | Done | bar: 2025-12-07 to 2026-03-29
4.3 | HTML and PHP Coding Back End | 2026-12-07 | 2026-03-28 | Done | bar: 2025-12-07 to 2026-03-29
4.4 | System Testing | 2026-03-28 | 2026-04-11 | Done | bar: 2026-03-29 to 2026-04-11
4.5 | Debugging | 2026-03-28 | 2026-04-12 | Done | bar: 2026-03-29 to 2026-04-12
5 | QA & Testing
5.1 | Multiple Device Test | 2026-04-12 | 2026-04-12 | Done | bar: 2026-04-12
5.2 | Beta Testing | 2026-04-13 | 2026-04-13 | Done | bar: 2026-04-13
6 | Deployment & Maintenance
6.1 | Authoring Privacy Policies and User Manual | 2026-04-13 | 2026-04-13 | Done | bar: 2026-04-14
6.2 | Deployment | 2026-04-14 | 2026-04-14 | Done | bar: 2026-04-15
6.3 | Maintenance | 2026-04-15 | 2026-04-15 | Done | bar: 2026-04-16
7 | Documentation
7.1 | Chapter 1: Introduction | 2025-11-29 | 2025-12-13 | Done | bar: 2025-11-29 to 2025-12-13
7.2 | Chapter 2: Review of Related Literature and Studies | 2025-12-06 | 2026-01-10 | Done | bar: 2025-12-06 to 2026-01-10
7.3 | Chapter 3: Methodology | 2026-01-10 | 2026-03-06 | Done | bar: 2026-01-10 to 2026-03-07
7.4 | Chapter 4: Results and Discussion | 2026-03-13 | 2026-04-01 | Done | bar: 2026-03-13 to 2026-04-01
7.5 | Chapter 5: Conclusion | 2026-04-01 | 2026-04-15 | Done | bar: 2026-04-01 to 2026-04-15
7.6 | Final Paper Check
7.7 | Defense
7.8 | Pareto Analysis